## Sheet1
WEEK 4: Line of Balance Diagram
Desired output rate, R | 3 | sections/week
Repeated units, n | 20
Working hours per day | 8 | hrs
Working days per week | 5 | days
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | Start | Start Last Unit | End Last Unit | End First Unit
Activity | Manhours per Unit | Men per gang | Theoretical Gang size at the chosen output rate, G | Actual Gang size, G_a | Actual output rate, R_a | Activity Duration for one unit | Time from start on first unit to start on last unit | Minimum buffer time | Buffer applied
A | 100 | 4 | 7.5 | 8 | 3.2 | 3.125 | 29.6875 | 5 | After 1st unit | 0 | 29.6875 | 32.8125 | 3.125
B | 350 | 6 | 26.25 | 24 | 2.7429 | 7.2917 | 34.6354 | 5 | After 1st unit | 8.125 | 42.7604 | 50.0521 | 15.4167
C | 60 | 2 | 4.5 | 4 | 2.6667 | 3.75 | 35.625 | 5 | After last unit | 20.4167 | 56.0417 | 59.7917 | 24.1667
D | 200 | 5 | 15 | 15 | 3 | 5 | 31.6667 | 5 | After last unit | 33.125 | 64.7917 | 69.7917 | 38.125
E | 150 | 8 | 11.25 | 16 | 4.2667 | 2.3438 | 22.2656 | 5 |  | 52.526 | 74.7917 | 77.1354 | 54.8698
[10 empty] | 82.1354 | 82.1354 | 82.1354 | 82.1354
Duration | 77.1354
0
20
20
0